Project Planning Phase

Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points)

| Date | 31 October 2025 |
| --- | --- |
| Team ID | NM2025TMID01076 |
| Project Name | Laptop Request Catalog Item |
| Maximum Marks | 5 Marks |

Product Backlog, Sprint Schedule & Estimation

| Sprint | Functional Requirement | User Story Number | User Story / Task | Story Points | Priority | Team Member |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Catalog Item Creation | USN-1 | As an admin, I can create a Service Catalog item named “Laptop Request.” | 3 | High | G S Akshaya |
| Sprint 1 | Variable Configuration | USN-2 | As a developer, I can add catalog variables (Laptop Model, Justification, Accessories). | 3 | High | Ishwariya M |
| Sprint 2 | UI Policy & Dynamic Behavior | USN-3 | As a developer, I can configure a UI Policy to show/hide “Accessories Details” based on selection. | 4 | High | Gopika Pillai K |
| Sprint 2 | UI Action Implementation | USN-4 | As a developer, I can implement a “Reset Form” UI Action to clear all inputs. | 2 | Medium | Gopika Pillai K |
| Sprint 3 | Update Set Deployment | USN-5 | As an admin, I can export and import the update set between instances. | 3 | High | Jabisha E |
| Sprint 3 | Testing & Validation | USN-6 | As a tester, I can verify all catalog item functionalities and variable behavior. | 3 | Medium | G S Akshaya |
| Sprint 4 | Documentation | USN-7 | As a developer, I can document the project design, testing, and planning phases. | 2 | Medium | Gopika Pillai K |

Project Tracker, Velocity & Burndown Chart:

| Sprint | Total Story Points | Duration | Sprint Start Date | Sprint End Date | Story Points Completed | Sprint Release Date |
| --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | 6 | 3 Days | 23 Oct 2025 | 25 Oct 2025 | 6 | 25 Oct 2025 |
| Sprint 2 | 6 | 3 Days | 26 Oct 2025 | 28 Oct 2025 | 6 | 28 Oct 2025 |
| Sprint 3 | 6 | 2 Days | 29 Oct 2025 | 30 Oct 2025 | 6 | 30 Oct 2025 |
| Sprint 4 | 2 | 1 Day | 31 Oct 2025 | 31 Oct 2025 | 2 | 31 Oct 2025 |

Velocity:

Average Velocity = Total Story Points Completed/Total Duration = (20/9) = 2.22 story points/day

Burndown Chart Summary:

The burndown chart shows steady progress across sprints, with all tasks completed within planned timelines. Each sprint met its target story points, maintaining consistent velocity and efficient project flow. The documentation phase was completed on 1st November 2025, marking the successful closure of the project.